## Strategic Plan Progress Tracker
Strategic Plan Progress Tracker
Item Type | Goal | Item | Milestone Year | Status
Goal | Goal 1 | Increase Access to Safe, Effective, Sustainable Pest Management |  | In Progress - on schedule
Sub-Goal | Goal 1.1 | Develop Public and Private Partnerships and Collaborations for Implementing Sustainable Pest Management | 2025 | In Progress - on schedule
Objective | Goal 1.1 | By 2025, establish a diverse, cross-sector SPM advisory group for advising on SPM implementation. | 2025 | Complete or Ongoing
Objective | Goal 1.1 | By 2025, in collaboration with CDFA and other partners and with public input, compile a list of certifications of agricultural and pest management practices, such as organic certifications, consistent with SPM, and develop a process for documenting IPM/SPM practices for California-grown produce. | 2025 | In Progress - on schedule
Objective | Goal 1.1 | By 2025, in collaboration with state and local agencies and with public input, develop a cross-agency plan for accelerating public sector sustainable pest management. | 2025 | In Progress - on schedule
Objective | Goal 1.1 | By 2028, develop SPM documentation for urban settings. | 2025 | In Progress - on schedule
Sub-Goal | Goal 1.2 | Improve timeliness and transparency of science-based evaluation and registration of pesticide products. |  | In Progress - on schedule
Objective | Goal 1.2 | By 2025, issue timeline projections for scientific data evaluations. | 2025 | Complete or Ongoing
Objective | Goal 1.2 | By 2025, create an accelerated pathway for the registration of feasible alternatives to priority high-risk pesticides and tools that cover pest management gaps. | 2025 | Complete or Ongoing
Objective | Goal 1.2 | By 2026, initiate pesticide registration evaluations within 30 days of receiving necessary information. | 2026 | In Progress - on schedule
Objective | Goal 1.2 | By 2027, update and clarify current data requirements for new pesticide technologies. | 2025 | In Progress - on schedule
Sub-Goal | Goal 1.3 | Develop and implement a science-based prioritization process for reviewing, identifying and evaluating high-risk pesticides, their alternatives and related mitigation measures. |  | In Progress - on schedule
Objective | Goal 1.3 | By 2025, annually release a report that includes a list of pesticide risk assessments, reevaluations and mitigation efforts, and progress toward meeting their identified target completion dates. | 2025 | Complete or Ongoing
Objective | Goal 1.3 | By 2025, establish a science-based pesticide prioritization process, informed by a diverse, cross-sector advisory committee, external engagement, and public input, to prioritize pesticide use risks, identify and evaluate the availability and feasibility of alternatives, and take expeditious action for completing mitigation. | 2025 | Complete or Ongoing
Objective | Goal 1.3 | By 2025, initiate reevaluation for at least one pesticide each year, increasing to at least two pesticides each year in 2029. | 2024 | In Progress - on schedule
Objective | Goal 1.3 | By 2025, where DPR has identified potential adverse effects through a reevaluation, adopt any necessary mitigation measures within two years. | 2026 | In Progress - on schedule
Sub-Goal | Goal 1.4 | Facilitate and support SPM technical assistance and innovation in pest management in collaboration with all interested partners. | 2025 | In Progress - on schedule
Objective | Goal 1.4 | By 2025, increase the number of integrated pest management and SPM technical assistance resources that DPR provides by 10% each year. | 2025 | Complete or Ongoing
Objective | Goal 1.4 | By 2025, establish formal partnerships with researchers, pest management practitioners, and IPM technical advisors to increase SPM technical support. | 2025 | Complete or Ongoing
Objective | Goal 1.4 | By 2025, invest in more proposals to test, research, and demonstrate pest management tools, knowledge, and practices that advance SPM. | 2025 | Complete or Ongoing
Objective | Goal 1.4 | By 2025, in partnership with CDFA and UC ANR, increase by 300 the number of Pest Control Advisors trained in sustainable pest management crop practices as part of a holistic approach to reducing pest pressures. | 2025 | In Progress - on schedule
Objective | Goal 1.4 | By 2027, evaluate success in transitioning to SPM through analysis of high-risk pesticide use and sales, reported pesticide-related illnesses, environmental monitoring, and other data and information in a publicly-reported annual summary. | 2027 | In Progress - on schedule
Objective | Goal 1.4 | By 2025, in partnership with CDFA and UC ANR, double the availability of DPR-accredited continuing education credits for Pest Control Advisors that address SPM practices in California. | 2025 | In Progress - delay
Goal | Goal 2 | Track, Evaluate, and Enforce Safe Pesticide Use |  | In Progress - on schedule
Sub-Goal | Goal 2.1 | Enhance and modernize DPR's collection of information and data to improve program policies, procedures, and priorities. |  | In Progress - on schedule
Objective | Goal 2.1 | By 2024, develop metrics for analyzing compliance trends and regulatory effectiveness across pesticides, repeat violations, repeat violators, application methods, and counties. | 2025 | Complete or Ongoing
Objective | Goal 2.1 | By 2025, establish ongoing ecosystem monitoring and collect information on the impacts of pesticide applications to organisms in the environment, targeting areas most impacted by pesticide use and providing timely public access to the monitoring data and information. | 2025 | Complete or Ongoing
Objective | Goal 2.1 | By 2025, establish transparent, local monitoring projects to track pesticides in water and air, designed in partnership with community representatives. | 2025 | Complete or Ongoing
Objective | Goal 2.1 | By 2028, expand DPR’s pesticide use data collection and trend analysis to include urban and other nonagricultural uses. | 2025 | In Progress - on schedule
Sub-Goal | Goal 2.2 | Enhance DPR’s statewide regulatory capacity in partnership with the County Agricultural Commissioners (CACs). |  | In Progress - on schedule
Objective | Goal 2.2 | By 2024, evaluate regulations governing pesticide use around schools to inform additional actions to support safe pest management around schools. | 2025 | Complete or Ongoing
Objective | Goal 2.2 | By 2026, increase number of oversight inspections by 10% and increase collaboration with CACs on county and state pesticide use enforcement activities to strengthen pesticide use compliance, to address repeat violations and offenders, and to inform mitigation measures. | 2026 | In Progress - on schedule
Objective | Goal 2.2 | By 2026, develop and annually offer a training academy for CAC staff biologists. | 2026 | In Progress - on schedule
Objective | Goal 2.4 | By 2027, update and implement pesticide use enforcement response policies and regulations to support statewide consistency and improve outcomes for all Californians, with a focus on disadvantaged communities impacted by pesticide use. |  | In Progress - on schedule
Sub-Goal | Goal 2.3 | Enhance statewide enforcement of pesticide sales laws. |  | In Progress - on schedule
Objective | Goal 2.3 | By 2025, formalize guidance for annually selecting companies to audit. | 2024 | Complete or Ongoing
Objective | Goal 2.3 | By 2025, increase number of pesticide mill audits by 25%. | 2025 | Complete or Ongoing
Objective | Goal 2.3 | By 2026, expand focus on e-commerce enforcement to more effectively regulate online sales. | 2025 | In Progress - on schedule
Objective | Goal 2.3 | By 2026, create a product compliance inspection framework for new, emerging alternative pesticides. | 2026 | In Progress - on schedule
Sub-Goal | Goal 2.4 | Improve worker safety by increasing awareness and reducing potential for pesticide exposure. |  | In Progress - on schedule
Objective | Goal 2.4 | By 2024, assess pesticide use violation data and by 2027, develop penalty guidance for CACs to enhance deterrence of pesticide worker safety violations. | 2025 | In Progress - on schedule
Objective | Goal 2.4 | By 2025, expand efforts to coordinate and collaborate with a broad range of stakeholders representing and serving those who work with or near pesticides, such as community-based organizations, CAC offices, community health workers and organizations, and growers to provide training and resources to migrant and other workers in multiple languages. | 2025 | In Progress - on schedule
Objective | Goal 2.4 | By 2025, increase collaboration with CalOSHA and other agencies with enforcement authority for pesticide exposures. | 2025 | In Progress - on schedule
Objective | Goal 2.4 | By 2028, adopt additional worker safety regulations to enhance compliance for training and documentation requirements, including for Farm Labor Contractors. | 2026 | In Progress - on schedule
Goal | Goal 3 | Foster Engagement, Collaboration and Transparency |  | In Progress - on schedule
Sub-Goal | Goal 3.1 | Broaden opportunities for regular, transparent, and meaningful access to DPR to increase awareness of and inform department programs, decision-making and actions. | 2025 | In Progress - on schedule
Objective | Goal 3.1 | By 2025, increase the number of meaningful outreach and engagement events, in accessible formats, including factors such as multiple languages, culturally relevant materials and information, event timing and locations known and accessible to interested parties, on: Pesticide use, pesticide safety and sustainable pest management for broader reach in agricultural and urban areas. Pesticide regulation, new and evolving pest pressures and effectiveness of available pest management alternatives, and sustainable pest management for broader reach in agricultural and urban areas and with regulated groups. |  | In Progress - on schedule
Objective | Goal 3.1 | By 2025, strengthen relationships with California Native American tribes by promoting and supporting efforts to expand environmental programs through culturally relevant, meaningful engagement, training, targeted outreach, technical assistance, and consultation. |  | In Progress - on schedule
Objective | Goal 3.1 | By 2026, establish and convene the Environmental Justice Advisory Committee. |  | Complete or Ongoing
Sub-Goal | Goal 3.2 | Improve information access and data sharing to increase transparency and awareness and understanding of California’s pesticide regulatory structure and sustainable pest management approaches. |  | In Progress - on schedule
Objective | Goal 3.2 | By 2024, streamline submission of public comments to DPR and provide public access to all public comments received by DPR. |  | In Progress - on schedule
Objective | Goal 3.2 | By 2025, redesign the department’s website to improve user experience and access to regulatory actions and documents, health and safety information, sustainable pest management resources, and other information and materials. | 2025 | Complete or Ongoing
Objective | Goal 3.2 | By 2026, implement new data visualization tools for stakeholders to interact with Pesticide Use Report data and at least two additional key DPR datasets. | 2025 | In Progress - on schedule
Objective | Goal 3.2 | By 2026, develop plain language guidance for DPR staff. |  | In Progress - on schedule
Sub-Goal | Goal 3.3 | Launch a statewide system (SprayDays California) to provide the public with advance information about restricted material pesticide applications. |  | Complete or Ongoing
Objective | Goal 3.3 | By 2024, finalize the regulation to implement SprayDays California statewide. | 2024 | Complete or Ongoing
Objective | Goal 3.3 | By 2024, engage and collaborate with stakeholders in advance of system launch to inform outreach and education associated with SprayDays. | 2025 | Complete or Ongoing
Objective | Goal 3.3 | By 2025, launch SprayDays California statewide, including engaging with interested parties. | 2025 | Complete or Ongoing
Objective | Goal 3.3 | By 2026, and through 2028, annually engage with DPR’s Environmental Justice Advisory Committee and the State Board of Food and Agriculture, and host a public comment period, to collect input on the system. | 2026 | In Progress - on schedule
Sub-Goal | Goal 3.4 | Expand language access throughout California in collaboration with federal, state and local stakeholders and partners. |  | In Progress - on schedule
Objective | Goal 3.4 | By 2024, provide resource support for county-based language access and increased community engagement. |  | Complete or Ongoing
Objective | Goal 3.4 | By 2025, assess language access needs, including Indigenous languages, across department programs to expand and enhance connection points, services, resources, and safety information offered by DPR. |  | Complete or Ongoing
Objective | Goal 3.4 | By 2025, establish collaborations with community-based health organizations to share information on pesticide safety training and enforcement. | 2025 | In Progress - on schedule
Objective | Goal 3.4 | By 2026, provide 100% of all health and safety resources in Spanish, and 75% of resources in at least one other language. |  | In Progress - on schedule
Objective | Goal 3.4 | By 2028, offer Spanish language exams for Qualified Applicators Licenses and Certificates. | 2025 | In Progress - on schedule
Goal | Goal 4 | Promote Organizational Excellence and Innovation |  | In Progress - on schedule
Sub-Goal | Goal 4.1 | Create and nurture a culture that supports and motivates excellence and professional development in workplace performance. |  | In Progress - on schedule
Objective | Goal 4.1 | By 2024, start reviewing and updating hiring and recruitment practices to foster a diverse applicant pool for open positions and promotional opportunities at DPR, and continue reviewing and updating as needed. | 2024 | Complete or Ongoing
Objective | Goal 4.1 | By 2025, increase pathways for staff involvement and leadership within the broader professional community. | 2025 | Complete or Ongoing
Objective | Goal 4.1 | By 2025, increase by 10% the total number of trainings offered across the department to support staff professional development. | 2025 | Complete or Ongoing
Objective | Goal 4.1 | By 2026, improve employee satisfaction in department communication and engagement by 10%. | 2026 | In Progress - on schedule
Sub-Goal | Goal 4.2 | Increase organizational efficiency and innovation. |  | In Progress - on schedule
Objective | Goal 4.2 | By 2024, launch initial California Pesticide Electronic Submission Tracking (CalPEST) system to submit pesticide registration applications. | 2026 | Complete or Ongoing
Objective | Goal 4.2 | By 2024, begin to provide modern hybrid workspaces to enhance in office and remote staff collaboration. | 2024 | Complete or Ongoing
Objective | Goal 4.2 | By 2025, complete transition to CalPEST for all pesticide registration processes. |  | Complete or Ongoing
Objective | Goal 4.2 | By 2025, begin development of electronic payment and online submittal of licensing applications, and by 2028, implement electronic system. |  | In Progress - on schedule
Objective | Goal 4.2 | By 2025, increase cross department and cross agency collaboration with partners at the local, state, tribal, and federal level on pest management initiatives. | 2025 | In Progress - on schedule
End of Spreadsheet
End of Spreasheet